## Sheet1
Risk Analysis
Description of Risk | How we will control the risk if it occurs | Risk Calculation
|  | Impact (out of 5) | Likelihood (out of 5) | Risk Score (impact * Likelihood) | Risk Level
Team member is often absent or not contributing - As we don’t all know each other, or how we all work, this is a high risk at the beginning of the project | Other team members will have to contribute a higher amount, and take on a higher work load. This will affect other modules. | 3 | 3 but later becomes a 2 | 9 then 6 | medium
Learning to use Android Studio - All team members are having to learn new development software. This is a risk that people will not take time to learn it. | The team member that doesn’t learn the software will have to take on other tasks, such as paperwork. | 3 | 2 | 6 | medium
Not being able to use the APIs we will be reliant on | We will not be able to complete theproject without these | 5 | 2 | 10 | medium
The final applicaton doesn’t work. | This will mean the project has been unsuccessful | 5 | 2 | 10 | medium