## Sheet1
Risk Analysis
Description of Risk | How we will control the risk if it occurs | Risk Calculation
|  | Impact (out of 5) | Likelihood (out of 5) | Risk Score (impact * Likelihood) | Risk Level
Team member is often absent or not contributing - As we don’t all know each other, or how we all work, this is a high risk at the beginning of the project | Other team members will have to contribute a higher amount, and take on a higher work load. This will affect other modules. | 3 | 3 but later becomes a 2 | 9 then 6 | medium
Learning to use Android Studio - All team members are having to learn new development software. This is a risk that people will not take time to learn it. | The team member that doesn’t learn the software will have to take on other tasks, such as paperwork. | 3 | 2 | 6 | medium
Not being able to use the APIs we will be reliant on | We will not be able to complete theproject without these | 5 | 2 | 10 | medium
The final applicaton doesn’t work. | This will mean the project has been unsuccessful | 5 | 2 | 10 | medium
Insufficient time for QA testing | Schedule enough time in advance to avoid it | 3 | 2 | 6 | medium
Lack of/no communication | Schedule weekly meetings where we update eachother and discuss next steps/progression | 4 | 2 | 8 | medium
Google charging for Firebase services | Have alternative plans if we need to hop services | 5 | 1 | 5 | low
Mistake on version control leads to loss of code | Make sure everyone is familiar and competent with github processes before we start. Following tutorials beforehand and maybe having a dummy repo to practice on. | 5 | 2 | 10 | high
<5 = Low
6-10 = Medium
>10 = High